## Sheet1
TASK DETAIL | TASK TYPE | ALLOCATED TO | STATUS | REMARKS | ALLOCATION DATE | END DATE | COMPLETION DATE | ALBERT | CLARIFICATION REQUIRED | CODING
Create excel sheet for task allocation | MANAGEMENT | UMAMAHESWARAN | COMPLETED | Uploaded in github | 2016-10-17 | 2016-10-23 | 2016-10-17 | BENJAMIN | COMPLETED | DESIGN
Create class diagram | DESIGN | UMAMAHESWARAN | NOT STARTED |  | 2016-10-17 | 2016-10-23 |  | DANIEL | IN PROGRESS | MANAGEMENT
KT to team on coding standard | MANAGEMENT | UMAMAHESWARAN | NOT STARTED |  | 2016-10-17 | 2016-10-23 |  | DI | NOT STARTED | POC
Interface qt with arduino/rasp-pi | DESIGN | Pamir | IN PROGRESS |  | 2016-10-17 | 2016-10-22 |  | EZEQUIEL | NOT APPLICABLE | REPORT
Design 3D turn table | DESIGN | Pamir | IN PROGRESS | Plans to collaborate with other teams for a common turn-table | 2016-10-17 |  |  | LUCA | REALLOCATED | RESEARCH
Studying and developing a crop-function | CODING | LUCA | NOT STARTED | Required for letting other groups working on that |  |  |  | NAYEE MUDDIN KHAN |  | TESTING
Studying and developing a crop-function | CODING | ROBERTO | NOT STARTED |  |  |  |  | PAMIR |  | UI DESIGN
Research documentation for PCL | RESEARCH | LUCA | IN PROGRESS |  |  |  |  | ROBERTO
Research on PCL 1.8\found all-in one installer | RESEARCH | LUCA | COMPLETED |  |  |  |  | SAVINIEN
Improvement of cropping to make it meshable | CODING | SAVINIEN | IN PROGRESS |  |  |  |  | UMAMAHESWARAN