## GanttChart
| 2016-10-09 | 2016-10-16 | 2016-10-23 | 2016-10-30 | 2016-11-06 | 2016-11-13 | 2016-11-20 | 2016-11-27 | 2016-12-04 | 2016-12-11 | 2016-12-18 | 2016-12-25
RESEARCH, POC & TRAINING | bar: 2016-10-09 to 2016-10-30
DESIGN | bar: 2016-10-16 to 2016-10-30
CODING | bar: 2016-10-23 to 2016-11-27
TESTING | bar: 2016-11-13 to 2016-12-11
USER MANUAL & REPORT | bar: 2016-11-27 to 2016-12-18

## Milestone Output
RESEARCH, POC & TRAINING
Research on sensor and its SDK
Research on Point cloud registration and processing
Mesh generation algorithm
Hardware interfacing from Qt(Turn table)
Sample code snippets based on feasibility study
Team trained on github, trello, coding standards
DESIGN
Design documents
- Usecase diagram
- Class diagram
- UI design
CODING
Source code of application with below features
- Scan an object/model to get point cloud
- Control the turn table and sensor to get different scans
- Point cloud registration
- Generate watertight mesh
- Graphical User Interface
- Import/Export point cloud and mesh
- Additional features
TESTING
Functional test results
USER MANUAL & REPORT
User manual
Final report and presentation
Updated design documents